## Sheet1
MINUTES OF THE MEETING
Topic for the Meeting : |  |  | Indices Automation Task Updates |  |  |  | Date : | 2022-04-26
[7 empty] | Meeting No. : | 1
Schedule Time of Start : |  |  | 15:00 | Actual Time of Start : |  | 15:15 | Venue : | Virtual
Planned Duration of the Meeting : |  |  | 1 Hr | Actual Duration of the Meeting : |  | 30 Minutes | Attendance (%) : | 33.33
Chaired By : |  |  | Chandrashekhar Kalashetti
Meeting Attended By : |  |  | Vikas T S, Pandurang, Bidhubhusan
Members Absent : |  |  | Rishabh Nigam, Vinod Kumar S
Invitees : |  |  | Rishabh Nigam, Vinod Kumar S, Vikas T S
Prepared / Recorded By : |  |  | Pandurang and Bidhubhusan
Additional Copies To : |  |  | Chandrashekhar Kalashetti
S No. | Task | Task Owner/Developer | Effort in hours | Planned Start Date | Actual Start Date | Progress Comments | Planned End Date | Actual End Date | Task Status
1 | Archive task | Rishabh Nigam | 32 | 2022-04-27 | 2022-04-27 | Completed | 2022-05-04 | 2022-05-10 | Completed
2 | excel-conversion | Vinod Kumar S | 40 | 2022-04-28 | 2022-04-28 | working on excel-part | 2022-05-05 | 2022-05-11 | In Progress
3 | login-authentication | Vikas T S | 28 | 2022-04-29 | 2022-04-29 | working login part | 2022-05-06 | 2022-05-12 | Not Started